1. BACKGROUND

The proposed Training of Trainers (ToT) program aims to equip 1,200 trainers across Punjab, Khyber Pakhtunkhwa (KP), Sindh and Baluchistan with the knowledge, digital skills and facilitation techniques required to deliver effective training to beneficiaries of the Benazir Income Support Program (BISP). The program will support a national target of 1 million (10 lakh) beneficiaries, with provincial targets determined by the agreed distribution. The training will use a one-day, in-person classroom model of 2–4 hours, with a strong emphasis on digital content, practical demonstrations, participant engagement and consistent delivery of the approved curriculum.

2. TRAINING DELIVERY APPROACH

A Digital Competency-Based, practice-oriented ToT model will be incorporated, following the sequence: Explain, Digital Demonstration, Practice, Teach Back, and Assess. This approach moves beyond lecture-based instruction by enabling trainers to understand the content, demonstrate relevant digital processes, practice facilitation techniques, and assess participant learning. The training will be delivered in easy language and visual demonstrations to support trainers working with beneficiaries who have varying levels of digital literacy.

| Training Model | Digital competency-based and practice-oriented Training of Trainers (ToT) |
| --- | --- |
| Duration | One-day classroom training, with approximately 2–4 hours of instructional time |
| Delivery Modality | In-person training at provincial and district levels, as per the approved rollout plan and Training manual |
| Training Facilitators | Master Trainers will lead the ToT and ensure consistency in content, methodology, and learning outcomes |
| Core Learning Approach | Explain → Demonstrate → Practice → Teach Back → Assess |
| Digital Learning Component | Live demonstrations, guided digital exercises, practical simulations, and scenario-based learning |
| Language and Accessibility | Simple language, locally understandable examples, visual aids, and step-by-step instructions to accommodate varying levels of digital literacy |
| Assessment and Quality Assurance | Practical competency checks, observation, feedback, and standardized assessment criteria to evaluate trainer readiness |
| Expected Outcome | Trainers equipped with technical understanding, practical digital skills, and facilitation competencies needed to deliver effective beneficiary-level training. |

The ToT will emphasize practical demonstrations of digital learning materials, interactive classroom exercises, beneficiary engagement techniques, and assessment methods to ensure consistent and high-quality training delivery across all four provinces.

3. IMPLEMENTATION STRATEGY

The implementation will proceed simultaneously across the eight operational zones. A batch size of approximately 30-40 trainers will be taken to facilitate meaningful participation, practical exercises, and micro-teaching. Implementation will include four key steps: (i) Preparation—finalizing the curriculum, training material, assessment tools, logistics, and Master Trainer orientation (ii) Parallel Delivery—conducting standardized sessions with attendance and progress tracking (iii) Competency Verification—assessing trainers’ knowledge, digital skills, and facilitation abilities before deployment and (iv) Consolidation— Conducting follow-up sessions to address common questions and learning gaps, reviewing training quality.

The beneficiary rollout will follow the three planned phases: Phase I (Pilot), targeting 250,000 beneficiaries with 300 trainers; Phase II (Scale-up), targeting 400,000 beneficiaries with 480 trainers; and Phase III (Completion), targeting 350,000 beneficiaries with 420 trainers. The ToT schedule prepares trainers in advance of their assigned deployment phase.

The proposed model combines standardized national content with practical, digital-first learning and locally responsive facilitation. Successful implementation will depend on parallel delivery, qualified trainers, digital resources, standardized assessments and continuous quality assurance.

4. PEER EDUCATOR MODEL

The Peer Educator Model will extend learning beyond classroom sessions by providing community-level guidance and reinforcement. Selected and trained peer educators (can be from the Bene cohort) will support beneficiaries through practical demonstrations, guided digital practice, local-language communication, and follow-up assistance.

Beneficiaries who demonstrate confidence and willingness to support others could be encouraged to act as peer educators, subject to an appropriate selection and onboarding process (either formally or informally).

The model will include:

- Identifying willing participants who demonstrate understanding of key concepts

- Providing them with simple, illustrated learning materials

- Train them to reinforce key messages and encourage safe digital practices

- Encouraging them to support other women through informal learning and supervised practice

The implementation will follow a three-tier approach;

| Peer Approach |  |  |
| --- | --- | --- |
| Tier 1: Masters Trainers | Capacity Building and Standardization | Equip Trainers with standardized training content, digital competencies, facilitation techniques, and guidance on supervising peer educators |
| Tier 2: Trainers | Training Delivery and Supervision | Deliver structured classroom training, identify and onboard suitable peer educators, monitor peer-learning activities, and provide technical guidance and follow-up support |
| Tier 3: Peer Educators | Community-Level Learning Reinforcement | Support fellow beneficiaries through practical demonstrations, guided digital practice, local-language communication, informal learning, and continued peer engagement. |

5. TARGETs AND TRAINERS DISTRIBUTION

The allocation of trainers is proposed in proportion to each province’s share of the 1 million beneficiary target. This creates a clear link between trainer deployment and the expected scale of beneficiary training.

| Sr | Component | Details |
| --- | --- | --- |
| 1 | National Target | 1,000,000 (10 Lakh) |
| 2 | Trainers to be Trained | 1,200 |
| 3 | Geographical Coverage | 04 Provinces i.e. Punjab, KP, Sindh & Baluchistan |

5.1. Provincial Trainers Distribution:

The provincial allocation of the 1,000,000 beneficiaries across the four provinces proposes the deployment of 1,200 trainers, distributed according to each province’s share of the overall beneficiary target is as follows;

| Sr | Province | Bene Target | Target Share (Proposed) | Required Trainers |
| --- | --- | --- | --- | --- |
| 1 | Punjab | 400,000 | 40% | 480 |
| 2 | KP | 300,000 | 30% | 360 |
| 3 | Sindh | 260,000 | 26% | 312 |
| 4 | Baluchistan | 40,000 | 4% | 48 |
| Total |  | 1,000,000 | 100% | 1,200 |

The provincial allocation of trainers has been determined in proportion to each province’s share of the national beneficiary target of 1,000,000. Punjab accounts for 40% of the target, equivalent to 400,000 beneficiaries, for which 480 trainers are proposed. Khyber Pakhtunkhwa (KP) represents 30% of the target, covering 300,000 beneficiaries, with 360 trainers required. Sindh accounts for 26% of the target, equivalent to 260,000 beneficiaries, supported by 312 trainers. Balochistan represents the remaining 4%, covering 40,000 beneficiaries, with 48 trainers required. This proposed proportional allocation of 1,200 trainers is designed to ensure equitable provincial coverage and alignment of training resources with the planned beneficiary outreach.

Planning assumption: Trainer numbers are distributed proportionately to provincial beneficiary targets. Final deployment will be validated against travel distances, trainer availability, field capacity and beneficiary caseloads.

5.2. Provincial and Zonal Deployment Plan

The following is a proposed initial allocation across the eight zones. Since actual zone-wise beneficiary caseloads have not been provided, the trainer distribution is divided evenly within each province for planning purposes.

| Sr. | Province | Zone | Trainers | Bene Target per Zone |
| --- | --- | --- | --- | --- |
| 1 | Punjab | North | 160 | 133,333 |
|  |  | Central | 160 | 133,333 |
|  |  | South | 160 | 133,333 |
| 2 | KP | North | 180 | 150,000 |
|  |  | Central | 180 | 150,000 |
| 3 | Sindh | Zone 1 | 156 | 130,000 |
|  |  | Zone 2 | 156 | 130,000 |
| 4 | Balochistan | Zone 1 | 48 | 40,000 |
| Total |  | 8 Zones | 1,200 | 1,000,000 |

The proposed allocation of 1,200 BISP trainers across four provinces and eight operational zones is aligned with provincial beneficiary targets to support equitable coverage and effective training delivery nationwide.

Punjab will be allocated 480 trainers (40% of the national pool), distributed equally across the North, Central and South zones, with 160 trainers per zone. Each zone will cover approximately 133,333 beneficiaries, with the South Zone assigned 133,334 to achieve the provincial target of 400,000. Khyber Pakhtunkhwa (KP) will receive 360 trainers (30%), divided equally between the North and Central zones, with 180 trainers and an indicative target of 150,000 beneficiaries per zone, totalling 300,000. Sindh will be allocated 312 trainers (26%), equally distributed between Zone 1 and Zone 2, with 156 trainers and a target of 130,000 beneficiaries per zone, totalling 260,000. Balochistan will receive 48 trainers (4%), assigned to Zone 1 to cover 40,000 beneficiaries.

6. PHASED TOT DEPLOYMENT PLAN

| Sr. | Province | Pilot (Phase – I) 250,000 | Sacle-Up (Phase – II) 400,000 | Completion (Phase – III) 350,000 | Total Trainers | Total Bene |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Punjab | 120 (40 each Zone) | 192 | 168 | 480 | 400,000 |
| 2 | KP | 90 (45 each Zone) | 144 | 126 | 360 | 300,000 |
| 3 | Sindh | 78 | 125 | 109 | 312 | 260,000 |
| 4 | Balochistan | 12 | 19 | 17 | 48 | 40,000 |
| Total |  | 300 | 480 | 420 | 1200 | 1,000,000 |

The proposed phased deployment of 1,200 BISP trainers is structured around three implementation phases to achieve the national target of training 1,000,000 beneficiaries. Phase I (Pilot) will deploy 300 trainers to support 250,000 beneficiaries, including 120 in Punjab, 90 in KP, 78 in Sindh, and 12 in Balochistan. Phase II (Scale-Up) will allocate 480 trainers to reach 400,000 beneficiaries, while Phase III (Completion) will deploy the remaining 420 trainers to cover 350,000 beneficiaries. Overall, the allocation comprises 480 trainers for Punjab, 360 for KP, 312 for Sindh, and 48 for Balochistan, aligned with their respective provincial targets of 400,000, 300,000, 260,000, and 40,000 beneficiaries.

This allocation establishes a clear framework for Provincial and Zonal deployment, implementation planning and performance monitoring, supporting the national target of training 1,000,000 BISP beneficiaries. Final deployment may be refined in line with operational requirements and beneficiary distribution.