PROJECT PROPOSAL

DFLT Phase Ⅱ- 2025

National Roll out of Digital and Financial Literacy Training, DFLT Program (BISP)

&

Adapting Livelihoods to Climate Change in Sindh

KEY DETAILS:

Document: Project Proposal

Submitted by: Sr. Research Fellow & Head-Center of Adaptive Social Protection

& Economic Empowerment

Head-Center of Evidence Action Research

Sustainable Development Policy Institute, SDPI

Contact Details: (009251) 2278134, 0300-9104104

Email:  fareehaarmughan@sdpi.org

Table of Contents

List of Abbreviation	3

1.	Background	4

2.	project Objectives/outcomes	5

3.	Geographic location	5

Size and scope	5

4.	Roles & Logistics	6

5.	Overview of Program Structure Across Targets	7

6.	Selection of third-party beneficiaries	8

QA Evaluators and Enumerators	8

7.	Methodology and Implementation Plan	9

7.1	Training of Trainers (Tot)	9

7.2	Rollout of training to Beneficiaries	9

7.2.1	Role of DFLT IC	10

7.3	Mobile Money Account Opening	11

7.4	DFLT Informational Video Intervention	12

8.	03 Intervention Under Sindh Chapter (Output 5)	13

Intervention 01-Mamta+Advanced DFLT Program	13

Intervention 02- Sindh Agriculture Women Worker Program	13

Intervention 03- Urban Informal Workers	14

Saving Scheme Follow up and Monitoring	15

9.	Beneficiary Journey Mapping (BJM)	16

9.1	In depth Interviews	17

10.	Digital system	17

11.	Quality Assurance	17

12.	Theory of Change	18

13.	Sustainability	19

14.	Project Products	19

Human Resource HR/Project Team & Staff	19

Selection of QA Evaluators	19

Roles and Responsibilities of Senior Research Fellow	20

Requirement of Hall for CASPEE	20

Annexure	20

Province wise Distribution of Coordinators	20

Mobility Allowance of DFLT IC	20

Payment Breakdown of Coordinators	20

# List of Abbreviation

DFLT	 Digital Financial & Literacy Training

SDPI 	 Sustainable Development and Policy Institute

KPK 	 Kyber Pakhtunkhwa

ASPC 	 Adaptive Social Protection Coordinators

PC	 Provincial Coordinators

DFLT IC   DFLT Implementation Coordinators

UC 	Union Council

M&E 	Monitoring and Evaluation

QA 	Quality Assurance

SRSO       Sindh Rural Support Organization

SSPA     Sindh Social Protection Authority

GIZ      Deutsche Gesellschaft für Internationale Zusammenarbeit (Development Partner)

# Background

New technologies are bringing access to financial services to the marginalized and under-served.  Banks and non-banks are introducing services and products to enhance the access to financial services. Yet around 1.7 billion adults of world lack access to financial services. Despite sustained efforts over the last decade, access to financial is on the lower side in developing countries. Evidence suggests that gender gap exists in financial inclusion. Women living, compared to men, are about 70% less likely to have access to financial services in developing countries.

The gap is even higher in Pakistan where already a very low share of population has access to finance. Millions of females do not have access to basic financial services of deposits, savings, credits and payments in rural geographies of Pakistan (Global Findex, 2021). The dilemma exists, nationwide, in all the five provinces of Pakistan (Punjab, KPK, Sindh, GB and Baluchistan) where already a very low share of population has access to finance. A report of world bank estimates that only 21 percent of the Pakistanis are financially included, against global and south Asian average of 69 and 33 percent respectively.

The Access to Finance survey (A2F), conducted by State Bank of Pakistan highlighted the significant gender difference in access to finance in Pakistan; the survey found that women remained less likely to gain access to the overall financial sector, compared to men. Notably, fewer women have access to banking services (5.5 percent vs. 21.1 percent men), Money transfers (1.4 percent vs. 3.3 percent men) and Insurance (0.6 percent vs. 3.3 percent men).

The problem severely effects the women and effects of financial exclusion go much beyond than not having saving account or not able to do online payments. Financial exclusion is negatively associated with women empowerment. Indigenous research shows that 94% of the women who do not have access to financial services have multidimensional social exclusion. In other words, these women are excluded from education, employment, and other dimensions of life. Exclusion from the spheres of education and employment further leads to the issues of social immobility, deeper poverty, low confidence, and low recognition in household status. Especially the illiteracy of mothers impacts the education of their children.

In Pakistan, the dilemma is more exacerbated concerning the women of the destitute, especially the ones falling under social protection program of BISP, living below the poverty line. The women who are enrolled in the umbrella of BISP beneficiary’s social safety net are mostly uneducated, marginalized, pro poor and disadvantaged segments of the society. This deep financial exclusion exists due to a major demand side gap of financial and digital illiteracy and a supply side gap of lack of infrastructure by financial service providers (FSPs).

The lack of education and financial illiteracy pose challenges, aggravating the dire conditions for those below the poverty line, especially women, as governments struggle to provide basic facilities. Commercial banks also show weaknesses in addressing these issues, hindering the inclusion of the impoverished and disadvantaged in the financial loop.

To address financial illiteracy and financial exclusion, Benazir Income Support Program, BISP launched the Digital and Financial Literacy Training (DFLT) Program, specifically designed to empower its beneficiaries in 2024. The DFLT Phase-I, 2024 provisioned financial literacy training to around 250,000 beneficiary women across 404 geographical locations spanning across the provinces of Punjab, Sindh, Khyber Pakhtunkhwa, and Balochistan. The overall purpose of the Digital financial literacy training is to enable BISP beneficiaries to do better financial planning; better management of their financial resources, improve their financial decisions, and access financial products and services available through the formal financial sector.

The DFLT Phase-1 also leveraged a parallel impact evaluation (Randomized Control Trial, RCT), under which an extended Baseline survey was undertaken for the purpose of providing a comprehensive understanding of the beneficiaries’ knowledge pre and post DFLT interventions. The Impact Evaluation incorporates robust methodology, and structured surveys have been administered across eight districts and sixteen tehsils, ensuring a representative nation-wide sample of the diverse BISP beneficiary population. Furthermore, to ensure that DFLT Phase-1 training adheres to established standards and achieve desired outcomes, a comprehensive Monitoring & Evaluation framework was devised. To ensure training quality, SDPI evaluators conducted rigorous M&E across training sessions nationwide

Building on the successful implementation of DFLT-Phase I, we recommend the National Rollout of DFLT Phase II (2025). Phase II aims to significantly expand training coverage to 550,000 women beneficiaries and simultaneously facilitate the opening of beneficiary formal bank accounts. This program rollout will further enhance the training horizon of the beneficiaries by subsequent dissemination of multiple DFLT informational videos after the classroom training.

This implementation plan outlines the detailed strategy and steps for conducting the Digital Financial Literacy Training (DFLT) program for the targeted beneficiaries of the Benazir Income Support Programme (BISP)

# project Objectives/outcomes

The objectives of the project are;

1. To provide Digital and Financial Literacy Training to 550,000 Social Protection beneficiaries across 04 provinces of Pakistan.

2. To open 300,000 Mobile Money Accounts of Beneficiaries who have received DFLT training under the Sindh Chapter.

3. To integrate multiple vertical interventions of Financial and Digital Literacy and Women Empowerment progressively in the province of Sindh such as imparting co-contributory saving scheme through registered mobile wallets to Women Agriculture Workers and Urban Informal Workers.

# Geographic location

## Size and scope

The National Roll Out Strategy for DFLT Phase Ⅱ (2025) will target 550,000 beneficiary women across Pakistan. This includes the BISP beneficiaries, SSPA beneficiaries of MAMTA program, Sindh Agriculture Women Workers and Urban Informal Workers. The Roll out comprises of two segments, imparting DFLT training to 250,000 BISP beneficiaries in 04 provinces of Pakistan and an additional segment of training 300,000 beneficiaries under Sindh Chapter.

National Roll Out: Under this overall segment, 250,000 beneficiaries will be imparted digital and financial literacy training across four provinces; Punjab, Sindh, Baluchistan and KPK. The beneficiaries will be imparted Digital and Financial Literacy Training structured on 02 days classroom model and community-based model across four provinces (Punjab, Sindh, Baluchistan and KPK). The training delivery mechanism will trickle down to the Union Council (UC) level, ensuring community-level reach and inclusion. The training will further factor in ‘Rural-Urban segmentation’ for the proposed sample where the target will be 50% rural and 50% urban locations. 30,000 beneficiaries in this overall segment will be from Sindh, while the remaining beneficiaries from other three provinces of Pakistan.

Moreover, the training will be coupled with concurrent account opening of the beneficiaries to ensure their digital and financial inclusion. The program targets at opening  300,000 mobile money accounts, in total, for the beneficiaries in Sindh.

The Sindh Chapter- The rollout of DFLT Phase-Ⅱ majorly focuses on the Sindh province. Out of 550,000 beneficiaries, 300,000 beneficiaries will be trained in Sindh only. These 300,000 beneficiaries include 165,000 Agriculture Women Workers in the flood prone districts of Sindh (Thatta, Badin, Sajawal & Sanghar); 125,000 MAMTA beneficiaries of Sindh Social Protection Authority in the 15 districts of interior Sindh (Ghotki, Jacobabad, Kamber Shahdadkot, Kashmore, Matiari, Mirpurkhas, Shikarpur, Tando Allah Yar, Tando Mohammad Khan, Tharparkar, and Umer Kot) and 10,000 Urban Informal Workers of Karachi, Sindh. In addition to the DFLT trainings, mobile money accounts will also be opened for the beneficiaries in Sindh. The roll out in Sindh also includes the intervention of enrolling 25,000 beneficiaries (15,000 Agriculture Women Workers and 10,000 Urban Informal Workers of Karachi) into co-contributory saving scheme. This saving scheme that comes with the co-contribution will encourage saving habit among beneficiaries and foster long term stability by providing financial security. Also, the saving scheme has certain conditionalities to be fulfilled by the beneficiaries, in order to attain the matching contribution.

# Roles & Logistics

Role of SDPI

The National Roll Out for DFLT Phase Ⅱ (2025) is to be devised and implemented by SDPI across four provinces. A project team at SDPI comprising of multiple tiers of resource persons/staff will ensure the roll out of Phase-II trainings along with the Sindh Chapter. SDPI will also be organizing a refresher training of the potential 560 Adaptive Social Protection Coordinators, ASPCs. The provision of complete resource material for training of beneficiaries including DFLT handbooks and informational videos will also be the responsibility of SDPI. Further there will be Live Dashboards for live and digital tracking of the DFLT Roll Out & Quality Assurance activities.

Provision of DFLT Handbooks / Training Material- The printing of 300,000 DFLT Handbooks was budgeted under the approved technical proposal versus the total target of 550,000. BISP was supposed to arrange 250,000 Books for the DFLT target of BISP Beneficiaries through a procurement process. However, this did not materialize and BISP wasn’t able to provide 250,000 books for DFLT.  Subsequently, to facilitate DFLT BISP chapter, SDPI with the approval of GIZ, handed over 110,000 books to BISP under the National Roll Out. Due to this facilitation, Sindh Chapter handbook stock depleted. In this regard, as per number of trainings left 35,000 additional DFLT Handbooks are demanded for Sindh Chapter.

Role of BISP & SSPA

The BISP Tehsil offices/BISP HQ  will be responsible for the arrangement of training venues for beneficiaries to achieve the DFLT targets, within the specified UCs of the Tehsil. There’s a requirement that BISP arranges the venues and shares the data of the potential beneficiaries of the phase II trainings (with SDPI) which will be exclusive of 250, 000 beneficiaries who have already received training during the roll out of DFLT program 2024.

Another role  of

Beneficiary data management will be facilitated dynamically through the ‘SDPI DFLT App’. BISP will be requested to initially provide partial beneficiary lists aligned with monthly training targets. Once ASPCs complete training sessions and submit attendance records, the app will automatically prompt BISP to replenish the beneficiary data, ensuring a new batch is added when existing data reaches a 30% depletion threshold. This real-time, incremental data-sharing mechanism will ensure efficient training operations and accurate beneficiary tracking.

# Overview of Program Structure Across Targets

The program aims to train 250,000 BISP beneficiaries nationwide through approximately 20,000 two-day classroom trainings at the Tehsil/Union Council (UC) level over a period of one year. This nationwide rollout of training will be carried out by the Adaptive Social Protection Coordinators ASPCs as per their geographical location. A pair of 02 ASPCs at Tehsil/UC level will be imparting training to cohort of 30-40 women through 02 sessions of 2-Days training per week. The total of 60-80 beneficiary women will be trained at one location by a pair of ASPC by conducting 02 trainings per week.

These ASPCs will be supervised by 40 DFLT Implementation Coordinators who will be physically covering and managing 03 districts/locations on the average. Each DFLT IC is responsible for managing 30 ASPCs organized in the pair of 15, overseeing 120 trainings per month. These DFLT ICs will report to their respective Provincial Coordinators, PCs stationed at the province Level. Furthermore, for the other core objective of 300,000 Mobile Money Account Opening, the agent network of the procured mobile money service provider (Firm under agreement) will reach out to the DFLT-trained beneficiaries; open; biometrically verify . To reinforce the formal account opening, a designated Financial Inclusion Coordinator-Account Opening at SDPI will be in place who will be coordinating and liaising with the  contracted mobile money service provider (Firm) and SRSO (Mobilizing Partner) for achieving account opening target. The Financial Inclusion Coordinator will ensure the operations and process at head office level.

The nationwide rollout strategy of DFLT Phase Ⅱ (2025) begins with the Training of Trainers (ToT) of ASPCs and DFLT ICs which will subsequently work to train the targeted beneficiaries through the 2-day classroom model. Simultaneously, the Financial Inclusion Coordinator at HQ level will start coordinating with the contracted Firm and SRSO to liaise the smooth account opening of the beneficiaries.   In order to enhance the learning spectrum of the training, a significant number of beneficiaries will receive additional DFLT informational videos on the key themes of digital and financial literacy over-time. From the research perspective, the project will perform the Survey of Key Performance Indicators/Beneficiary Journey Mapping by quantitative or qualitative data collection from the trained beneficiaries to assess their training experiences and outcomes. Lastly, there will be extensive quality assurance of the trainings by the Quality Assurance team of SDPI specifically trained for this project.

# Selection of third-party beneficiaries

For the successful implementation of the project, the following third-party beneficiaries will be selected:

## QA Evaluators and Enumerators

Quality Assurance Evaluators and Enumerators will be selected from SDPI's available list and advertisement process, considering factors such as survey experience, CVs, district, proficiency with smartphones and tablets, educational qualification (Minimum Qualification: FSC), and availability. A competitive selection process will be conducted to ensure the best candidates are chosen. SDPI will provide training to the evaluators for monitoring, and successful candidates will be onboard for the project. Moreover, training will be provided to the enumerators for beneficiary journey mapping.

The selection process will be fair, transparent and non-discriminatory. Evaluators will be selected mainly from Sindh, and each evaluator will be tasked to evaluate and perform spot checks for on ground Trainings; Saving scheme; Mobile money account opening and Mobilisation. For trainings, each evaluator will be present during entire duration from start to end and ensure training is delivered across all its pillars. Further, Enumerators will be selected across 4 provinces for conducting quantitative or qualitative data collection from the trained beneficiaries to assess their training experiences and outcomes. Further, they will also facilitate in the Focus Group Discussions and In-depth Interviews (explained in the Beneficiary Journey Mapping Section).

# Methodology and Implementation Plan

The proposed implementation plan involves series of steps. Here is the detailed breakdown of each step of project intervention.

## Training of Trainers (Tot)

In the first quarter of the National Rollout of DFLT Phase Ⅱ (2025), there will be full one day, online Refresher session for the ASPCs. The refresher training will be for ASPCs, inclusive of previous ASPCs of Phase-1 and new ASPCs recruited to manage the increased beneficiary coverage and target achievement across Pakistan, especially in Sindh. For the refresher Punjab, Sindh and KPK provinces will be divided into 3 zones and Baluchistan into 1 zone.

The trainings equip the ASPCs with necessary knowledge and skills required to train the beneficiaries on key aspects of; Digital and Financial Literacy, Bank management, Budgeting, Bank account opening, Saving, Investment, Climate Change and Disaster Risk Reduction, Gender Equality and BISP’s broader objectives on financial inclusion and social protection. It also includes introduction of ASPCs with the corresponding DFLT ICs, roles and responsibilities and working alignment. After 4 months, another refresher training will be conducted online to reinforce the learning experience, address field implementation challenges, and maintain training quality.

## Rollout of training to Beneficiaries

After the Refresher training, Adaptive Social Protection Coordinators, ASPCs will start training the beneficiaries in their respective Tehsils/Duty stations. These will be ASPCs from DFLT 2024 and new ones designated to duty stations to conduct DFLT trainings in 8 months across Pakistan. The ASPCs will provide training in a pair and each pair will teach a cohort of 30-40 women in a 2-day training classroom model. Each pair will conduct 2 trainings per week for a period of first four months with each training spanning over two consecutive days. Both the ASPCs (belonging to a pair) must be present on both days of trainings, as they will rotate roles between teaching and administrative responsibilities to ensure balanced workload distribution and maintain efficiency. All the ASPCs will be equipped with necessary material for training including tablets and DFLT handbooks.

The DFLT trainings will be leveraged to beneficiaries through a set of interventions. The DFLT will also focus upon interactive role play sessions; group activities that will help to practice skills such as using banking services, identifying currency notes, opening digital accounts, and managing budgets

Group Activities; It fosters peer support within groups, creating supportive environment for those feeling less confident. The participants get the opportunity to network potentially collaborating on financial initiatives. This not just ensures developing the social capital but information retention, cultivating the motivating atmosphere. The small group size of 30 beneficiaries per session is ideal for fostering personalized peer support.

Role Play Sessions; Engaging in interactive role play sessions with the help of the characters from the DFLT handbook,  Naila & Shumaila, Akbari & Asghari provides experiential learning and help internalize the concepts more efficiently. It significantly contributes to skill development and behavioural change, leading to increased confidence and competence in applying digital and financial literacy skills like numeracy, budgeting & saving concept in their daily lives.

Practical Demo Sessions; The ASPCs will provide the practical session of using calculator on feature phone and performing mobile wallet transactions. The beneficiaries will learn to perform basic arithmetic operation to improve their numeracy skills. Also, the practical session on mobile wallet transactions equips the participants with the skills to navigate digital payment platforms, promoting financial inclusivity & effective learning.

### Role of DFLT IC

The project will hire the 40 DFLT Implementation Coordinators, each of which will be responsible for managing 30 ASPCs organized in 15 pairs. Each DFLT IC will be overseeing trainings delivered by pair of  ASPCs spanning across minimum 3 adjacent /Tehsils to maximum 6 adjacent /Tehsils. The key roles and responsibilities of DLFT IC include;

- Supervise and monitor ASPC training schedule/logistics/data collection and establishing reporting line to provincial coordinators.

- Monitor progress towards account creation targets (bank accounts/mobile money accounts)

- Establish and maintain coordination for venues with BISP, schools (public & private) and ASPCs for training venue arrangements to set up the classroom model for 2 days training

- Ensure completion of beneficiary training targets and timely resolution of logistical and operational issues encountered in the field.

- Further, DFLT IC will also ensure timely and adequate delivery of DFLT Handbooks to ASPCs for final handing over to beneficiaries during training.

Mobility Schedule-Each DFLT IC has to travel 2 days per week to their adjacent districts for spot checks and monitoring of the trainings. The mobility schedule of each DFLT IC is given as;

Week 1: Home city monitoring

Week 2: First adjacent district

Week 3: Second adjacent district

Week 4: Third adjacent district

The first week will be not compensated for mobility allowance as each DLFT IC will be monitoring in their home city. In the remaining 3 weeks, they will travel for 2 days making it total of 6 travel days in a month. As there are 2 trainings per week and each training consisting of 2 days, the DFLT IC will spot check the day 1 of one training and day 2 of other while travelling to adjacent districts.

## Mobile Money Account Opening

The second target of DFLT Phase Ⅱ- Sindh Chapter (2025) is to open  300,000 mobile money accounts of all the DFLT-trained beneficiaries under the Sindh Chapter, across the 15 DFLT districts of Interior Sindh and Karachi. To facilitate the account opening of the beneficiaries, the SDPI will hire the Financial Inclusion Coordinator at HQ level. The financial inclusion coordinators at HQ level are responsible for;

- Liaise with the potential Firm for mobile account opening services at the selected training venues at the community level where the beneficiaries are physically present

- Coordinating and communicating with ASPCs and team  in field, along with the potential Firm and SRSO.

Revised Mobile Money Account Opening Modality- Under the earlier approved technical proposal, the opening of the mobile money accounts across the 04 provinces rested with the social protection authorities, BISP and SSPA, and their partner banks were supposed to open the accounts at the training venues at zero-cost. Accordingly, no specific budget line was established for this activity. However, with the announcement of the Prime Minister’s Digital Wallet scheme for BISP beneficiaries at the very inception of the DFLT Phase - II — whereby every BISP beneficiary is being provided a free social protection digital wallet along with a SIM — the account opening requirement for the BISP beneficiaries ceased to exist, and the entire account opening target has been routed to DFLT-II Sindh Chapter under the purview of the Government of Sindh. SDPI will now be facilitating this ToR by engaging a mobile money service provider (the ‘Firm’), selected through a competitive and transparent procurement process (guided by SDPI’s Management Procedures) for opening the mobile money accounts of 300,000 DFLT-trained beneficiaries across the 15 districts of Sindh and Karachi.

Role of SDPI- SDPI will provide the complete data of the beneficiaries, collected as part of the DFLT trainings — comprising the beneficiary’s name, CNIC, phone number, UC/village, tehsil and district — to the contracted Firm and to SRSO. SRSO will mobilise these women at the village level, while SDPI will coordinate in terms of sharing the effective and updated beneficiary data with both. Additionally, for the ongoing trainings, SDPI will provide the locations of the trainings to the Firm 3–4 days ahead of the training, so that the agent network of the firm reaches the Village level/Community venues in time and open the accounts on the spot.

Role of the Firm- It is the responsibility of the Firm and its agent network to reach the DFLT-trained beneficiaries on ground, at the community level where the beneficiary is physically present. The scope of the Firm covers the complete cycle of identification of the beneficiary, issuance of a SIM in the name of the beneficiary woman, opening of the mobile money account, biometric verification, and activation of the account. In case of the ongoing trainings, the Firm’s agents will visit the training venues. The ownership and control of the SIM and of the mobile money account will rest with the DFLT-trained woman herself. The Firm will also maintain a live data dashboard of the account opening and activation status, not merely for its own information but also for the information of SDPI and GIZ.

Before account opening, the beneficiaries will already be given the Digital and Financial Literacy Training and collected data against following key variables by ASPC. The key data points are;

- Mobile Ownership or Access (Who controls the account?)

- Mobile Type (Smartphone/Feature Phone)

- Bank Account Existence (Yes/No)

- Money Storage Preference (Bank/Mobile Wallet)

- Bank Account Openings (Newly created accounts)

- Willingness for enrollment in the contributory saving scheme

## DFLT Informational Video Intervention

This video intervention includes six sets of informational videos (06 focused on Savings and Investment, and 06 addressing Climate Change and Gender Equality), which will be shared with the beneficiaries over 12 weeks via WhatsApp groups, with one video sent each week. The videos are designed to provide knowledge about financial literacy, budgeting, climate change and gender equality in a structured way. These DFLT Informational Videos are titled around;

- Climate Action

- Gender Equality

- Financial Literacy

- Budgeting

- Feature Phone & Calculator

- Saving and Investment

By delivering the informational videos weekly, the program allows beneficiaries to enhance the learning spectrum, learn steadily, helping them absorb, retain and learn the content more effectively. This step-by-step approach also makes it easier to measure the overall impact of DFLT Phase II in achieving its objectives.

# 03 Intervention Under Sindh Chapter (Output 5)

This section outlines the details of 03 vertical interventions particularly tailored for the province of Sindh for a period of 2.5 years (14 June 2025 - 30 November 2027) as a part of national roll out of DFLT Phase-Ⅱ. These interventions are;

## Intervention 01-Mamta+Advanced DFLT Program

The basic Mamta Program, primarily executed by Government of Sindh is providing cash transfer at 16 touchpoints for 1000 days/ three years since conception. Under the first Intervention, the Digital and Financial Literacy Training will be imparted to 125,000 Mamta beneficiaries in 15 districts of; Badin, Ghotki, Jacobabad, Kamber Shahdadkot, Kashmore, Matiari, Mirpurkhas, Sanghar, Shikarpur, Sajawal, Tando Allah Yar, Tando Mohammad Khan, Tharparkar, Thatta and Umer Kot. These trainings will include modules on savings and micro-credit. The intervention also includes opening digital mobile accounts of the beneficiaries receiving DFLT training.

Mobilisation of the Mamta Beneficiaries- The mobilisation of the Mamta beneficiaries in 07 districts will be taken up by SRSO (Sindh Rural Support Organization), which has established field presence. In the remaining 04 districts — Tharparkar, Matiari, Tando Adam and Tando Allahyar — where SRSO does not have field presence, SDPI will itself undertake both the mobilisation of the beneficiaries and the arrangement of the training venues. SRSO was onboarded by GIZ in January 2026 for the reason that the identification of SSPA MAMTA beneficiaries is an intricate task, and a local organisation such as SRSO, carrying indigenous knowledge, and access to these communities is essential for convening them for the DFLT training.

## Intervention 02- Sindh Agriculture Women Worker Program

During. Subsequently in the following months, SDPI will impart the Digital and Financial Literacy Training to 165,000 female workers and open their mobile money account as part of the intervention of DLFT Phase-II. The 15,000 women out of these 165,000 will then be targeted for enrolment in the co-contributory saving scheme for the period of 09 months. This intervention will focus on the agriculture district(s) of Sindh. Based on the ground realities and implementation feasibility. The intervention will therefore specifically focus on, targeting the agriculture women workers in the agriculture districts of Sindh, and the enrolment will have a mix of women having ownership of the cell phone and access to cell phone, so that the control of the mobile money account rests with the woman herself. The Sindh government organization of SRSO will also be mandated to leverage additional benefits such as, asset transfer, microfinance, crop insurance, access to market and other, ensuring the long-term adaptation.

## Intervention 03- Urban Informal Workers

In Jan 2027 , HANDS (Health and Nutrition Development Society) will identify and register the urban informal workers in Karachi East/West/Central. Subsequently, SDPI will impart Digital and Financial Literacy Training to 10,000 informal workers and will facilitate opening of their digital mobile accounts through the onboarded firm. The intervention will also enrol these 10,000 workers into co-contributory saving scheme, ensuring co-contributory grant on the saving ≤ Rs 800/ month for period of 09 months.

Scope of HANDS- HANDS will identify, mobilise and register the urban informal workers of Karachi and will mobilize the registered beneficiaries to SDPI. SDPI will thereafter impart the Digital and Financial Literacy Training during February and March, following which the beneficiaries will be enrolled into the co-contributory saving scheme for a period of 09 months, running up to 31 December.

Urban Classroom Model and Venues- In rural Sindh, the trainings are delivered at any available space at village/community level. Karachi, being a metropolitan city, does not offer this. Also, the Urban Informal Workers are massively dispersed across multiple zones of the city. A prototype classroom model is therefore imperative for the urban landscape, under which dedicated training space will be arranged, zone-wise, across Karachi. To cover the 10,000 urban informal workers, 400 two-day trainings will be required at a cohort size of 25 beneficiaries per training.

## Saving Scheme Follow up and Monitoring

For the first intervention, training will be given to 125,000 Mamta beneficiaries in 8 months with parallel account opening. Similarly, for  3rd intervention, HANDS will register  the urban informal workers in  Jan 2027. In the next months, these workers will be imparted digital and financial literacy trainings with parallel account opening and enrolment in saving scheme.

Designated Field Offices- The saving scheme will be operated through designated offices per District. This office presence is not a matter of convenience but of operational necessity. At the very onset of the intervention, a retail agent cannot be taken, door to door, into the villages, as an itinerant agent collecting cash from women will be labelled a fraudulent actor

Digital Verification at Every Step- At every step of the enrolment in the saving scheme, the deposit of the saving into the mobile money account and verification cycle will be continuously digitized, so that the verification activity should converge from manual verification to digitized/phone verification over time through the 9 months of the scheme.

Licensed Retail Agents- SDPI will take into loop licensed Retail Agent at designated office(s) & selective spots in field, who will receive the saving amount from the beneficiaries and deposit it into their respective mobile wallets. After a certain initial period, t

There will be a follow up team of saving scheme stationed at SDPI and coordinating with the potential Firm and beneficiaries for confirmation/evidence of depositing saving into their accounts. Upon verification and confirmation of evidence, the SDPI finance team will be posting the co-contributory matching amount into their accounts quarterly over the 09 months of the scheme.  This follow up team will be engaged throughout the life of project for actively monitoring and coordinating with all the beneficiaries having different timelines of attaining the co-contributory saving scheme.

# Beneficiary Journey Mapping (BJM)

Journey Mapping is a valuable tool for understanding and improving the experiences of beneficiaries that underwent any social protection programs, service and systems. It is comprehensive approach that creates the roadmap of the beneficiary journey, highlighting touchpoints, challenges and opportunities for improvements. A study showed that Personas and Journey mapping is an essential tool that offers insights into complex nonlinear and interconnected experiences of beneficiaries within social and program contexts. Thus, employing this technique allows to better understand the impact of DFLT program and address the unique needs of the beneficiaries accordingly.

We recommend utilizing Focus Group Discussions (FGDs) as a qualitative approach to gather insights from the beneficiaries, trainers and the community on the overall experience of the DFLT program. We propose the following set of FGDs at household level across four provinces: Four focus group discussions will be conducted by the survey team- i) with beneficiaries who received training, ii) Household members of the beneficiaries who underwent training, iii) with a group of community leaders and iv) ASPCs/DFLT IC

The FGDs with beneficiaries who underwent training aims to assess the program's effectiveness, exploring their experiences, comprehension of digital tools, and any observed behaviour changes. The FGDs with the household of the beneficiaries reflect upon the any behavioural change as improved financial planning and decision making. Then engaging community members in FGDs provides valuable contextual insights, gauging the program's broader impact on the community. Lastly, the FGDs with ASPCs and DFLT IC will uncover the strengths and weakness of the intervention with on ground implementation. Combining these perspectives, the FGDs aims to offer a comprehensive understanding of the program's outcomes, strengths, and areas for improvement, informing evidence-based decisions for program enhancement and expansion.

## In depth Interviews

In addition to FGDs, in-depth interviews will be conducted to gather detailed information and insights from potential stakeholders. This allows for a broader exploration of the experiences and perspectives of participants, providing a richer understanding of the challenges and opportunities in leveraging the DFLT program. Moreover, the insights from the coordinators and evaluators will be crucial in shaping the targeted interventions under program rollout.

# Digital system

This section highlights how digital systems provided by BISP and SDPI will enhance the efficiency, transparency, and effectiveness of the program interventions

BISP- BISP will allocate tablets for facilitating the nationwide rollout of training to beneficiaries. The distribution of tablets is given as; for ASPCs and for DFLT ICs.

SDPI- SDPI will develop Live Status Dashboard of DFLT Training for 04 provinces. The live dashboard will be updated on a daily basis by data coming from the field. There will be 02 M&E Dashboards i-e Status Dashboard & M&E-CTO Dashboard. The ‘DFLT Digital App’ will be designed and will allow live monitoring and evaluation of the ASPCs and DFLT training sessions. It included digital attendance, live screen shots of training and Performa filling. Lastly, SDPI will provide the old tablets to QA Evaluators for M&E activities.

Leveraging digital systems for project interventions serves to improve the data management, ensures real time monitoring and evaluation, enhanced communication and coordination optimizing the overall project impact.

# Quality Assurance

For the rollout of DFLT Phase Ⅱ (2025), the M&E of 1000 DFLT Trainings Saving Scheme; Mobile Money Account Opening and Mobilisation by QA Evaluators is proposed. We will build on quality assessment process undertaken during DFLT Phase I 2024, where full day evaluation was done by SDPI evaluators team across 4 provinces in Pakistan. It included Survey CTO, M&E Performa designed in collaboration with UNICEF. Also, there were Live dashboards and M&E protocol which was then supervised by National & Provincial M&E coordinators at SDPI. The live dashboard has been designed and maintained to monitor the trainings, participants, enumerator and provincial output. Additionally, for efficient coordination and communication of M&E activities, real time updates and communication was set up through WhatsApp groups with SDPI core team and separate group for field teams in each province.

For the quality assurance process, there will be  Provincial Coordinators, Evaluators and Monitoring Support. The coordinators will be responsible for monitoring and guiding the evaluators on training and venues. They provide them with specific daily props and instructions tailored to regional needs. The Evaluators are required to visit designated training locations, conduct thorough assessments, and follow the instructions provided by the Provincial Coordinators. They will use Survey CTO to document findings accurately and in real time using the mobile phones.. A dedicated SDPI team ensures effective monitoring by tracking location coordinates and data quality through the Survey CTO app.

The trainings will be monitored across some key pillars to assess and evaluate the quality of DFLT in meeting its objectives. These pillars are;

- Clarity of content

- Relevancy of content

- Accessibility of content

- Communication skills

- Training methods

- Adherence to schedule

In the DFLT rollout for 2025, there will be additional DFLT IC overseeing and monitoring the trainings and ASPCs. So, if a DFLT Implementation Coordinator is monitoring trainings, our QA Evaluator will not conduct M&E for those sessions to avoid overlap.

# Theory of Change

The theory of change of the project is anchored in its core objectives of enhancing digital and financial literacy among beneficiaries and leading them to path of financial inclusion and economic empowerment. Here is the breakdown of interventions and expected outputs and outcomes.

# Sustainability

The sustainability of the project is embedded in its holistic interventions that ensures the financial inclusion of marginalized and under-served beneficiary women. Leveraging advanced digital and financial literacy training will enhance the awareness of beneficiary women and ensures informed decision making. The intervention of opening the registered mobile money accounts enables them to actively participate in formal financial services. Additionally, the enrolment in the saving scheme would serve as the stepping stone towards financial resilience. Overall, the approach promotes long term benefits by establishing the self-sustaining model that integrates the awareness building with access to financial services on the pathway towards financial inclusion.

# Project Products

- 550,000 trained BISP and SSPA beneficiaries in total

- 300,000 Account Openings

- Dissemination of set of DFLT Informational Video (12 videos developed during Impact Evaluation) to significant number of beneficiaries

- Implementation of 03 interventions of Sindh Outcome 5 Component.

- DFLT-Beneficiary Journey Mapping (field visit for qualitative data collection)

- Quality Assurance of DFLT-2025

- Project Report

# Work-Plan/Milestones

The timeline of the project will comprise of 29 months (14 June 2025 – 30 November 2027) while the submitted revised budget amounts to Euro ___________ (attached). The milestone-wise breakdown of the activities, reflecting the amended targets and the revised implementation modalities, is given as under;

| Name of the Project | Title: DFLT Phase II- 2025 — National Roll out of Digital and Financial Literacy Training, DFLT Program (BISP) & Adapting Livelihoods to Climate Change in Sindh |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone 1: [Implementation Design & Spade Work; Refresher Training of 560 ASPCs] |  |  |  |  |  |  |  |  |
| Activities | Mon 1 | Mon 2 | Mon 3 | Mon 4 | Mon 5 | Mon 6 | Mon 7 | Mon 8 |
| 1.1 Implementation Design/Groundwork/Onboarding | X | X |  |  |  |  |  |  |
| 1.2 Digital App & Dashboards development | X | X |  |  |  |  |  |  |
| 1.3 Designing of content for Handbook & Handbooks printing | X | X |  |  |  |  |  |  |
| 1.4 Refresher Training of 560 ASPCs & 40 DFLT ICs |  | X |  |  |  |  |  |  |
| 1.5 Competitive procurement & contracting of the Mobile Money Service Provider (Firm) |  |  |  |  |  | X | X | X |
| 1.6 Onboarding of SRSO by GIZ for mobilisation of MAMTA beneficiaries |  |  |  |  |  |  |  | X |
| Milestone 2: [Roll Out of DFLT Trainings Part-1 / Quality Assurance] |  |  |  |  |  |  |  |  |
| Activities | Mon 1 | Mon 2 | Mon 3 | Mon 4 | Mon 5 | Mon 6 | Mon 7 | Mon 8 |
| 2.1 Roll out of 02 DFLT Trainings per week (National & Sindh) |  |  | X | X | X | X | X | X |
| 2.2 Roll out of DFLT Trainings to MAMTA Beneficiaries (125,000) — SRSO mobilisation in 08 districts, SDPI mobilisation & venues in 04 districts |  |  | X | X | X | X | X | X |
| 2.3 Quality Assurance of DFLT Trainings |  |  | X | X | X | X | X | X |
| 2.4 Account opening liaison by Financial Inclusion Coordinator (HQ) with the Firm & SRSO |  |  |  |  | X | X | X | X |
| Milestone 3: [Roll Out of DFLT Trainings Part-2 / Mobile Money Account Opening / Quality Assurance] |  |  |  |  |  |  |  |  |
| Activities | Mon 9 | Mon 10 | Mon 11 | Mon 12 | Mon 13 | Mon 14 | Mon 15 | Mon 16 |
| 3.1 Roll out of DFLT Trainings to Agriculture Women Workers (165,000) in the flood prone districts | X | X | X | X | X | X | X | X |
| 3.2 Mobile Money Account Opening on ground by the contracted Firm — SIM issuance, biometric verification & activation (300,000 accounts) | X | X | X | X | X | X | X | X |
| 3.3 Deployment of Digital Account Facilitators (14 per district) bridging SRSO mobilisation & Firm account opening | X | X | X | X | X | X | X | X |
| 3.4 Quality Assurance of DFLT Trainings | X | X | X | X | X | X | X | X |
| 3.5 DFLT Informational Videos Intervention | X | X | X | X | X | X |  |  |
| 3.6 Beneficiary Journey Mapping (FGDs & In-depth Interviews) |  |  |  |  | X | X | X | X |
| Milestone 4: [Sindh Chapter Interventions & Follow Up of the Co-contributory Saving Scheme] |  |  |  |  |  |  |  |  |
| Activities | Mon 17 | Mon 18 | Mon 19 | Mon 20 | Mon 21 | Mon 22 | Mon 23 | Mon 24 |
| 4.1 Establishment of designated field offices, Saving Scheme Coordinators, Mobilisers & licensed Retail Agents | X | X |  |  |  |  |  |  |
| 4.2 Enrolment & follow up of 15,000 Agriculture Women Workers in the co-contributory saving scheme (09 months) | X | X | X | X | X | X | X | X |
| 4.3 Identification, mobilisation & registration of 10,000 Urban Informal Workers of Karachi by HANDS |  |  |  | X |  |  |  |  |
| 4.4 DFLT Trainings of Urban Informal Workers — 400 two-day trainings at a cohort size of 25 (zone-wise prototype classroom model) |  |  |  |  | X | X |  |  |
| 4.5 Enrolment & follow up of 10,000 Urban Informal Workers in the co-contributory saving scheme (09 months) |  |  |  |  |  |  | X | X |
| 4.6 Quarterly posting of the co-contributory matching amount by SDPI Finance |  |  | X |  |  | X |  |  |
| Milestone 4 (continued): [Follow Up of the Co-contributory Saving Scheme & Project Closure] |  |  |  |  |  |  |  |  |
| Activities | Mon 25 | Mon 26 | Mon 27 | Mon 28 | Mon 29 | Mon 30 |  |  |
| 4.2 / 4.5 Follow up of the co-contributory saving scheme — Agriculture Women Workers & Urban Informal Workers (25,000 in total) | X | X | X | X | X | X |  |  |
| 4.6 Quarterly posting of the co-contributory matching amount by SDPI Finance | X |  |  | X |  | X |  |  |
| 4.7 Digital verification of savings deposits — convergence from manual to digitised/phone verification | X | X | X | X | X | X |  |  |
| 4.8 Analysis & Project Final Report |  |  |  |  | X | X |  |  |

# Human Resource HR/Project Team & Staff

The hiring of staff, consultants, other HR etc. will be done through free and fair processes and in accordance with SDPI’s HR policies.

## Selection of QA Evaluators

Quality Assurance Evaluators will be selected from SDPI's available list, considering factors such as survey experience, CVs, district, proficiency with smartphones and tablets, educational qualification (Minimum Qualification: FSC), and availability. A competitive selection process will be conducted to ensure the best candidates are chosen. SDPI will provide training to the evaluators for monitoring, and successful candidates will be onboard for the project. The selection process will be fair, transparent and non-discriminatory.  The  evaluators will be selected across 4 provinces, and each evaluator will be tasked to evaluate on ground trainings. Each evaluator will be present during entire duration from start to end and ensure training is delivered across all its pillars.

## Roles and Responsibilities of Senior Research Fellow

The Senior Research Fellow (PhD) belongs to the senior management (Executive Status of ED/JED/DED) at SDPI and the role of Senior Research Fellow is to ensure deliverance of project objectives, overall quality assurance and completion of the project from the institutional side. The Senior Research Fellow will be continuously involved in the implementation of project in capacity of senior management for holistic and effective execution.

## Requirement of Hall for CASPEE

The hall (on rental basis) is required to setup Center of Adaptive Social Protection & Economic Empowerment (CASPEE), which was launched in Nov 2024. Essentially this center will implement the entire project. The whole team of the project will be sitting in this hall/center and coordinating across 4 provinces.

# Annexure

## Province wise Distribution of Coordinators

The project will hire ASPCs, currently the ASPCs from DFLT-Phase-1 are distributed across four provinces as follow (the table below reflects the Phase-I distribution of 673 ASPCs)

| Province | ASPC | DFLT IC | PC |
| --- | --- | --- | --- |
| Punjab | 261 | 12 | 1 |
| KP | 169 | 10 | 1 |
| Baluchistan | 131 | 5 | 1 |
| Sindh | 109 | 13 | 1 |
| Islamabad | 3 | 0 | 0 |
| Total | 673 | 40 | 4 |

## Mobility Allowance of DFLT IC

In the first week, DFLT IC will monitor in the home city and will not receive any mobility allowance. There will be six travel days of each DLFT IC in a month. The total mobility allowance of Rs. 150,000 lump sum for 10 months (15000/month) will be given to each DFLT IC. The amount will prorate will fewer travel days are completed.

## Payment Breakdown of Coordinators

All the coordinators including ASPCs, DFLT IC, PCs, Financial Inclusion Coordinatorswill get fixed monthly compensation as per SDPI payroll.

Amendment (31 July 2026). Original Proposal: the co-contributory saving scheme was provisioned for the 10,000 Mamta beneficiaries, 5,000 Agri Women Workers and 10,000 Urban Informal Workers. Now the revised target audience is 15,000 Agriculture Women Workers of Flood Prone District(s) of Sindh while the original specified target of 10,000 Urban Informal Workers of Karachi remains unchanged (25,000 in total). This revision has been undertaken as per instructions of GIZ and in consultation with SSPA. (Please refer to Section 8 for further details)

At the inception of the DFLT Phase 2 BISP chapter, BISP Scaled down this provincial target to 30,000 due to the consideration that a very massive number of 300,000 was being leveraged concurrently under DFLT - II Sindh Chapter

At the very onset of the project, The Prime Minister Wallet scheme got announced covering essentially the entire NSER comprising of 10 million BISP Beneficiaries. In lieu of the Prime Minister’s Wallet scheme, the account opening requirement of the BISP beneficiaries under the DFLT Phase - II National Roll Out stands addressed; the program now targets opening 300,000 mobile money accounts, in total, for the DFLT-trained beneficiaries of the Sindh Chapter (Please refer to Section 7.3 for more details).

Amendment (31 July 2026). Original Proposal: The 300,000 Sindh Chapter beneficiaries comprised 250,000 Mamta beneficiaries, 40,000 Agriculture Women Workers in the Flood prone districts (Thatta, Badin, Sanghar & Sajawal) and 10,000 Urban Informal Workers of Karachi and Hyderabad. Now, the allocations are revised to 165,000 Agriculture Women Workers in the flood prone districts of Sindh, 125,000 Mamta beneficiaries in the 11 districts of Interior Sindh, and 10,000 Urban Informal Workers of Karachi. The overall Sindh Chapter target of 300,000 remains unchanged. This revision has been undertaken after deliberations with GIZ and in consultation with SSPA.

Since the target of covering 165,000 in 4 Flood Prone districts of Sindh namely Badin, Thatta, Sajawal and Sanghar is massive so the MAMTA target (125,000 in total) will be covered relatively lesser in these 4 districts as compared to rest of the 11 MAMTA Districts.

As conveyed by GIZ, Urban Informal Workers is now specified to Karachi, East, West and Central zones.

These conditionalities concerning frequency of deposits without gaps, retention of saving in account and matching thresholds etc will be elaborated in consultation with social protection authorities prior to the program roll out.

Amendment (31 July 2026). Original Proposal: 616 Adaptive Social Protection Coordinators (ASPCs) were provisioned for the national roll out. Now, after the field implementation and anticipating future activities, the trainer strength stands rationalised to 560 ASPCs. The reduction arises from the revised deployment at the duty stations against the actual district and tehsil coverage; the consolidation of adjacent tehsils under trainer pairs and reappropriation of cohort size by upward revision over-time.

In original proposal, it was mentioned that “The BISP Tehsil offices/BISP HQ and SSPA (Sindh) will be responsible for the arrangement of training venues.” While during DFLT Phase - II, BISP adhered to this assigned ToR, SSPA regretted during the very planning phase of DFLT Phase - II that due to the constraint that SSPA tehsil office’s do not exist on ground & a very limited infrastructure is available at a district level so SSPA is not in a position to provide the required logistics of training venues & mobilization of MAMTA beneficiaries for DFLT Trainings. To Resolve the issue, SDPI, voluntarily took up the ToR of SSPA; of Mobilization of Agri Women Workers in 04 Flood Prone Districts. Since Mobilization of MAMTA beneficiaries is an complex task that requires indigenous knowledge & support of community mobilizer network, GIZ sorted this out and onboarded SRSO (Sindh Rural Support Organization), a very effective community mobilizer partner in the landscape of Sindh for mobilizing MAMTA benefeciaries in 07 Districts of Sindh. SDPI, further took up mobilization of MAMTA benefeciaries and provision of venues for additional 04 MAMTA districts where SRSO is not present on ground. These mobilization realities created constraints that later led to the bifurcation of the total MAMTA target of 250,000 to 165,000 Agri Women Workers & 125,000 MAMTA beneficiaries.

Amendment (31 July 2026) In Original Proposal, it was stated that “Role of BISP and SSPA (for Sindh) is to engage the partner banks for facilitating ‘Mobile Money Touch Points’ at the training venues across 04 provinces where the agents of partner bank will regularly visit and will open the mobile money accounts of the consenting beneficiaries on spot. “. The engagement of the partner banks for establishing ‘Mobile Money Touch Points’ at the training venues rested with BISP and SSPA, whose partner banks (under contract) were supposed to open the accounts at zero cost. Accordingly, no budget line was created for this activity in the approved budget of DFLT-II. In Section 3 (Size and Scope) we’ve explained the shift of BISP Mobile Money account opening to Sindh Chapter because of the Prime Minister Wallet Scheme. SSPA regretted from this ToR from the very onset of the DFLT Phase - II Implementation. Now, after deliberations of SDPI & GIZ, SDPI will enter into a contract with service provider firm after a competitive procurement process, where the service provider firm will openup mobile money accounts of DFLT trained women at Village/UC level & will also provide sims in the name of the women beneficiary. In this context, in the corresponding budget supplement a budget line is created for opening of mobile money account of 300,000 women beneficiaries. This decision making has been undertaken with GIZ and in consultation with SSPA. (Please refer to See Section 7.3. for more details).

Amendment (31 July 2026). Earlier the scope encompassed the opening of the accounts at the training venues by SSPA’s partner banks. Now, account opening by firm will be in line with the applicable regulatory requirements of biometric verification, mandatory by the State Bank of Pakistan’s Branchless Banking Regulations and the biometric SIM issuance requirements of PTA.

Original Proposal; “During the first 6 months of DFLT program roll out, the Sindh Rural Support Organization (SRSO) will identify and register female workers in agriculture with the Labor Department and Agriculture Department of Sindh.” As per the ToR’s of the original proposal, SRSO was supposed to perform the mobilization of Agri women Workers in Agri Women however this was a voluntary arrangement with the SRSO which did not execute as planned. SDPI then performed this task for mobilization of 165000 in Agriculture Districts.

Amendment (31 July 2026). Earlier: the Digital and Financial Literacy Training was to be imparted to 40,000 female agriculture workers, to be registered by SRSO within the first 06 months. Now: consequent to the revised composition of the Sindh Chapter (Section 3), the coverage stands enhanced to 165,000 Agriculture Women Workers across the flood prone districts of Sindh. This shift stands undertaken with the approval of GIZ and in consultation with SSPA.

Amendment (31 July 2026). Earlier, as per original proposal, 3,500 women out of the 40,000 DFLT Trained Agriculture Women Workers were to be enrolled in the saving scheme, in 04 districts (Badin, Sanghar, Sujawal and Thatta). Now: the enrolment stands enhanced to 15,000 Agriculture Women Workers and the area for the intervention will be Thatta alone or all the 04 Agricultural districts. The scope of intervention is based on the consideration of the limitation that very few agriculture women workers percentage holds cell phone ownership.

The beneficiaries in the 3rd wealth quintile will be given additional benefits for poverty graduation. Of the total beneficiaries, 10,000 will be targeted for micro-finance and crop insurance, while 1500 will be targeted for asset transfers and access to market. Also, community block grants will be provided to 20 COs for running a cash for work programme for mangroves reafforestation.

Amendment (31 July 2026). Original Proposal: the identification and registration of the urban informal workers was assigned to the Akhtar Hamid Foundation. Now: this responsibility rests with HANDS (Health and Nutrition Development Society), which will identify, mobilise and register the urban informal workers of Karachi and will mobilize the beneficiary to SDPI.

Amendment (31 July 2026). Original Proposal: the urban informal workers were to be identified and registered in Karachi East, Karachi West and Hyderabad. As per instructions of GIZ, the DFLT Trainings along with the saving scheme enrolment of 10,000, holds only for Karachi.

Amendment (31 July 2026). Original Proposal: the co-contributory grant was provisioned at a maximum saving ceiling of Rs. 1,000 per month per beneficiary. Now: as per guidelines by GIZ, the maximum monthly saving ceiling eligible for co-contribution is reduced to Rs. 800. The duration of the saving scheme is also reduced from 12 Months to 9 Months for the complete target of 25000.

Amendment (31 July 2026). Original Proposal: the saving scheme was to be followed up via phone by a limited team stationed at SDPI, with no field structure incorporated. Now: a field-based delivery system will be established — designated office(s), Field teams and licensed Retail Agents — as detailed in this section.

All the FGDs will be transcribed and synthesized upon completion

The beneficiaries will be convened at a particular venue where they will be interviewed collectively in a group. Tea and refreshment will be served during FGDs

(BISP was not able to provide ASPC’s the NSER linked tablets due to confidentiality limitations so SDPI had to improvise and leverage the DFLT app on cell phones )