FIELD IMPLEMENTATION, BENEFICIARY TRAINING & BEHAVIOURAL REINFORCEMENT

CONTEXT:

BISP is increasingly transforming its cash grant distribution inti digital and sim based distribution mechanisms. However, the BISP beneficiaries have low to zero digital financial knowledge, less familiarity with digital mobile services and SIM devices. These constraints make this digital transformation difficult for theses beneficiaries. This necessities the need to equip these beneficiaries to be equipped  with not only digital financial services but also with the practical knowledge to use these digitalized services confidently and effectively. And also to be aware of the transaction security and fraud.

This brings the need for a structured and behavior reinforcing Digital Financial Capability Trainings (DFCT) program that combines face-to-face learning with digital reinforcement and community-based support. The proposed strategy seeks to deliver structured digital financial capability training to 1 million BISP beneficiaries, while establishing a continuing reinforcement mechanism that enables beneficiaries to recall, practice and apply the skills acquired through training.

The proposed model moves beyond a conventional training approach towards a blended model integrating in-person face to face readiness and capacity trainings, reinforcing through digital content, instructional videos, SMS and IVR nudges, digital job aids, payment touchpoints, agent-level support and community-based reinforcement.

Rather than treating training as a single event, the program will establish a beneficiary learning journey extending from readiness in person face to face training, immediate post-training reinforcement through digital channel, practice and longer-term behavioral support followed with in person face to face capability training and immediate post training reinforcement.

This approach recognizes that beneficiaries differ considerably in terms of literacy, access to mobile phones, smartphone ownership, previous exposure to digital financial services and confidence in using technology. Accordingly, the program will be adapting communication and reinforcement mechanisms to beneficiaries' levels of device access and digital literacy.

The program will target 1 million BISP beneficiaries, with implementation coordinated closely with BISP's existing institutional structures, field teams, payment mechanisms and beneficiary outreach channels.

IMPLEMENTATION STRATEGY

TRAININIG OF THE TRAINERS (TOT):

The strategy of DFCT begins with the Training of Trainers (ToT) of 1200 DFCT trainers and DFCT ICs which will subsequently work to train the targeted beneficiaries through the 1-day classroom model.

These ToTs will equip the DFCT Trainers with necessary knowledge and skills required to train the beneficiaries on key aspects of; Digital and Financial Literacy and capacity trainings. It also includes introduction of DFCT Trainers with the corresponding DFLT ICs, roles and responsibilities and working alignment.  The details of these TOTs are discussed in section ……..

THE NATIONAL ROLL OUT OF DFCT TRAININGS:

To  equip 1 million beneficiaries with digital financial capability training, the target will be achieved by dividing the number of 1 million beneficiaries into three different phases. The first phase will be implemented over the period of 2 months, comprising of training 250,000 beneficiaries.

The 2nd phase will be implemented over a period of 4 months targeting 400,000 beneficiaries. The last and the 3rd phase will be targeting 350,000 beneficiaries spanning over a period of 4 months.

| PHASES | PHASE 1 | PHASE 2 | PHASE 3 |
| --- | --- | --- | --- |
| BENEFICIARIES TARGET | 250,000 beneficiaries | 400,000 beneficiaries | 350,000 beneficiaries |
| TIMELINE | 2 months | 4 months | 4 months. |

Please note that all the phases will be implemented on the same strategy that will be discussed in the subsequent section with different timelines set according to the target of number of beneficiaries to be trained. Each phase will be then accompanied by a review and course correction period for structured review of phase 1 implementation, accessing training quality, beneficiary turnover and participation, digital content dissemination and is effectiveness. Trainer performance will also be keenly evaluated in this time period.

To make it more structured, a correction course report will be presented to the awarding party or any other evaluating partner if designated, comprising of the tailored content and specific adjustments wherever needed after the critical review.

Each phase will be implemented in the following manner.

THE PHASE STRATEGY:

The first phase will be comprising over 2 months with the target of training and capability building of 250,000 beneficiaries. The second and third phase will be comprising over 4 months with the target of training and capability building of 400,000 and 350,000 beneficiaries respectively.  The training schedule will be implemented as per the following schedule.

The first month will be comprising of demonstrating readiness in person one to one 1 day training approach to the beneficiaries. The content of this 1 day in person training will be provided in the form of a short handbook / toolkit provided to the trainers and to the beneficiaries as well. Each trainer will conduct four trainings per week along with two days dedicated for mobilization of beneficiaries. It is to be noted that one cohort of beneficiaries will be entertaining 25 beneficiaries on average.

This one to one in person readiness  training will be followed by structured dissemination of digital content (IVR, short videos, SMS nudges) in the next four weeks. Precedently, the cohort trained on 1st day of the week i.e. on Monday will be provided with the digital content from the next day through the automated systems developed by the IT team of SDPI. This will ensure the implementation of a sequenced behavioral reinforcement through digital channels.

This will make in total of 16 trainings a month per trainer.

In the next month, the DFCT capacity one to one in person 1 day trainings of the same cohort of beneficiaries will be initiated. The capability trainings of beneficiaries will be scheduled on the same set of beneficiaries that have availed readiness one to one training in the first month. It will be assured that the beneficiary trained in the readiness training must undergo capacity training in the capacity-training month. Outliers can be adjusted sin case the need arises.

As soon as the beneficiary completes the in person capacity training, behavioral reinforcement will be done through the structured dissemination of the digital content of this capacity training (IVR, short videos, SMS nudges) in the next four weeks.

Since the 2nd and the 3rd phase will be targeting 400,000 and 350,000 beneficiaries respectively, therefore, the timelines for these phases will be extended to 3rd and 4th months respectively. The 3rd month of these phases will be again dedicated to readiness trainings and the 4th month will be dedicated to capability training of the remaining beneficiaries. The 2nd and the 3rd phase will be scaled upon the same strategy as of 1st phase.

| PHASE | MONTH | TYPE of TRAINING | Number Of Beneficiaries (spread across all four provinces) |
| --- | --- | --- | --- |
| 1st Phase (total 250,000 beneficiaries) | 1st month | Readiness Trainings | 250,000 |
|  | 2nd month | Capacity training | 250,000 |
| 2nd phase (total 400,000 beneficiaries) | 1st Month | Readiness Training of 1st Cohort | 200,000 |
|  | 2nd Month | Capacity Training of 1st Cohort | 200,000 |
|  | 3rd Month | Readiness Training of 2nd Cohort | 200,000 |
|  | 4th Month | Capacity training of 2nd Cohort | 200,000 |
| 3rd phase (total 350,000 beneficiaries) | 1st Month | Readiness Training of 1st Cohort | 175,000 |
|  | 2nd Month | Capacity Training of 1st Cohort | 175,000 |
|  | 3rd Month | Readiness Training of 2nd Cohort | 175,000 |
|  | 4th Month | Capacity training of 2nd Cohort | 175,000 |

ASSISTANCE AT PAYMENT TOUCHPOINTS:

A sequenced behavioral reinforcement program will integrate digital financial readiness and capability support into beneficiary interactions at payment points, in coordination with BISP and payment service providers. Key activities may include displaying visual safety messages, screening short educational videos where feasible, demonstrating secure transaction practices, conducting basic readiness checks, sharing information on official complaint and support channels, and referring beneficiaries facing access or transaction difficulties to relevant service providers. Dedicated team members (DFCT trainers) will also be oriented to reinforce consistent messages on fraud prevention, account security, and safe digital payment practices. Readiness checks may cover mobile phone and SIM availability, registered mobile number status, familiarity with security credentials, and awareness of support mechanisms. All activities will uphold beneficiaries’ consent, privacy, and confidentiality, ensuring that no PINs, passwords, or OTPs are requested or retained and that no unauthorized transactions are conducted. These payment-touchpoint interventions will complement formal training by reinforcing learning, addressing practical barriers, and promoting safe, confident, and independent use of digital financial services.

DIGITAL DATA RECORD:

Beneficiary data management will be facilitated dynamically through the ‘SDPI DFCT App’.   The DFCT trainers delivering the in person training will also be responsible for keeping beneficiary attendance record data of one to one in person training classroom model for both readiness and capability trainings. The trainers will submit this beneficiary attendance record through SDPI DFCT app. This real-time, incremental data-sharing mechanism will ensure efficient training operations and accurate beneficiary tracking. The influx of this beneficiary data record through the SDPI DFCT app will be connected with a customized dashboard developed by SDPI.

ROLE OF SDPI:

These training phases to be devised and implemented across four provinces of Pakistan namely Punjab, Sindh, Baluchistan and KPK. A project team at SDPI comprising of multiple tiers of resource persons/staff will ensure the roll out of these readiness and capacity training. . SDPI will also be organizing a refresher training of the potential 1200 DFCT trainers. The provision of complete resource material for training of beneficiaries including DFCT short handbooks/toolkit, flyers, digital informational videos, IVR and SMS nudges will also be the responsibility of SDPI. Further there will be Live customized Dashboards for live and digital tracking of the DFCT Roll Out & Quality Assurance activities.

IMPLEMENTATION COORDINATORS (ICs):

The project will hire DFCT Implementation Coordinators (ICs), each of which will be responsible for managing 15 DFCT Trainers on average. Each DFCT IC will be overseeing trainings delivered by  DFCT trainer spanning across minimum 3 to Maximum 6 adjacent Tehsils. Each DFCT IC is responsible for monitoring 16 trainings per month on average. The key roles and responsibilities of DFCT IC include;

- Supervise and monitor their respective training schedule/logistics/data collection and establishing reporting line to provincial coordinators.

- Establish and maintain coordination for venues with BISP, schools (public & private) and DFCT Trainers for training venue arrangements to set up the classroom model for 1 days training readiness and capability training model.

- Ensure completion of beneficiary training targets and timely resolution of logistical and operational issues encountered in the field.

- Further, DFCT IC will also ensure timely and adequate delivery of DFCT Toolkit/ short handbooks, printed flyers to DFCT Trainers for final handing over to beneficiaries during training.

Mobility Schedule-Each DFCT IC has to travel 2 days per week to their adjacent districts for spot checks and monitoring of the trainings. The mobility schedule of each DFCT IC is proposed as;

Week 1: Home city monitoring

Week 2: First adjacent district

Week 3: Second adjacent district

Week 4: Third adjacent district

PROVINCIAL COORDINATORS (PCs):

DFCT Implementation Coordinators (ICs) will report to their respective Provincial Coordinators (PCs). A designated Provincial Coordinator will be appointed for each province to oversee and coordinate program implementation at the provincial level. The Provincial Coordinators will be responsible for the following:

- Responsible for overseeing, supervising, and coordinating program implementation within their assigned provinces. Provincial Coordinators will ensure that training activities are conducted according to the approved implementation plan, timelines, and quality standards.

- Their responsibilities will include supervising DFCT ICs and trainers, reviewing training progress and digital monitoring reports, verifying beneficiary participation and training completion records, and ensuring timely reporting of implementation challenges.

- They will also track beneficiary engagement and feedback, identify recurring issues related to training delivery and coordinate with relevant officials to resolve operational issues.

- Based on monitoring findings, PCs will recommend and follow up on corrective actions, facilitate communication between field teams and program management, and ensure consistent training quality, effective beneficiary support, and the achievement of program targets across their respective provinces.

A designated Quality Assurance (QA) Team will be designated to monitor and evaluate the quality, consistency, and effectiveness of DFCT trainings across all implementation areas. The team will conduct regular monitoring through digital reporting systems, review training records and attendance, assess trainers’ performance and adherence to approved training materials, and provide timely feedback to address implementation gaps and improve training delivery.

A designated Digital Reinforcement Team will oversee digital reinforcement activities, including short educational videos, SMS nudges, and IVR/robocalls, to reinforce key digital financial capability  messages, promote safe digital transactions, raise awareness about fraud prevention, and encourage beneficiaries to apply the knowledge gained during training.

ROLE OF BISP:

The BISP Tehsil offices/BISP HQ  will be responsible for the arrangement of training venues for beneficiaries to achieve the DFCT targets, within the specified UCs of the Tehsil. There’s a requirement that BISP arranges the venues and shares the data of the potential beneficiaries of the DFCT trainings with SDPI and will also facilitate in mobilizing the beneficiaries for DFCT trainings.The program should leverage existing BISP systems and human resources wherever possible rather than creating parallel delivery structures.

Implementation may be organized geographically and operationally through BISP Structure involving

- BISP field offices and regional structures.

- Designated BISP Coordination Team.

- BISP Trainers/facilitators.

- BISP community-level outreach mechanisms.

- Payment service providers and agent networks.

Furthermore, for the other core objective of assisting transaction and facilitating beneficiaries, these DFCT trainers will also provide provide in-person support and facilitate beneficiaries at designated access touchpoints, particularly during the tranche disbursement period, to ensure timely assistance and smooth access to payment services.